## 30-Day Journey
EMPLOYEE ONBOARDING EXPERIENCE
Self-initiated process-design project ¦ Blank template; adapt to company policy
Phase | Task / milestone | Primary owner | Support owner | Target timing | Status | Priority | Notes / evidence
Preboarding | Confirm accepted offer, role, start date and point of contact | HR / recruiter | Hiring manager | Before start | Not started | High
Preboarding | Send first-day agenda, location/access information and contact details | HR / recruiter | Hiring manager | 3–5 days before start | Not started | High
Preboarding | Prepare equipment, accounts and required system access | IT | Hiring manager | Before start | Not started | High
Preboarding | Define role expectations and first-month priorities | Hiring manager | HR | Before start | Not started | High
Day 1 | Welcome, team introductions and organisation context | Hiring manager | HR / buddy | Day 1 | Not started | High
Day 1 | Complete required joining documents and policy orientation | HR | New hire | Day 1–3 | Not started | High | Use approved secure HR systems for documents
Day 1 | Confirm equipment, access and essential tools work | IT | New hire / manager | Day 1 | Not started | High
Week 1 | Review role responsibilities, success measures and key contacts | Hiring manager | Buddy | Week 1 | Not started | High
Week 1 | Schedule manager check-ins and relevant training | Hiring manager | New hire | Week 1 | Not started | Medium
Week 1 | Confirm mandatory learning and policy acknowledgements | HR | New hire / manager | Week 1 | Not started | Medium | Follow organisation policy
Week 2 | Check early questions, blockers and training needs | Hiring manager | HR | Day 7–14 | Not started | High
Week 2 | Confirm essential system access and required learning status | IT / HR | Hiring manager | Day 7–14 | Not started | Medium
Day 15 | Run two-week pulse check and record agreed actions | HR | New hire / manager | Day 15 | Not started | Medium | Record only necessary information
Week 3 | Review initial work, priorities and support needs | Hiring manager | New hire | Day 15–21 | Not started | Medium
Week 4 | Check team integration, workload and outstanding blockers | Hiring manager | Buddy / HR | Day 22–28 | Not started | Medium
Day 30 | Conduct 30-day review and gather new-hire feedback | Hiring manager | HR / new hire | Day 30 | Not started | High
Day 30 | Agree next-month goals and close or assign open actions | Hiring manager | New hire | Day 30 | Not started | High

## Document Checklist
JOINING DOCUMENT CHECKLIST
Template only. Follow local law and company policy; collect and store documents only through approved secure channels.
Document / requirement | Applicability | Owner | Target timing | Status | Secure record reference / notes
Signed offer / employment agreement | As applicable | HR | Before start | Not started
Identity / right-to-work checks | As legally required | HR | Before start or per policy | Not started
Payroll / tax setup details | As required | Payroll / HR | Before payroll cut-off | Not started | Use approved secure system; do not store sensitive details in this workbook
Bank / payment details | As required | Payroll / HR | Before payroll cut-off | Not started | Use approved secure system; never place account numbers here
Policy acknowledgements | Per organisation policy | HR | Day 1–7 | Not started
Emergency contact | If required by policy | HR | Per policy | Not started | Handle with appropriate access controls
Role-specific compliance / certifications | If role requires | Hiring manager / HR | Before duties requiring it | Not started

## Check-in Tracker
NEW-HIRE CHECK-IN TRACKER
Use respectful, job-related prompts; restrict access to notes and record only necessary information.
Check-in | Timing | Owner | Suggested prompts | Status | Action owner | Follow-up date
First-day pulse | Day 1 | HR | Does the new hire know where to go and whom to contact? Are tools/access working? | Not started
Week-one check | Day 5–7 | Manager / HR | Are role expectations, training, tools and key contacts clear? | Not started
Two-week check | Day 14–15 | HR | What is going well? What is unclear or blocking progress? | Not started
30-day review | Day 30 | Manager / new hire | Review early goals, integration, support needs and next steps. | Not started

## Guide & Measures
IMPLEMENTATION GUIDE & MEASURES
Topic | Guidance
Objective | Make the first 30 days clear, welcoming and trackable, with visible task ownership and planned check-ins.
Ownership principle | HR coordinates the process and policy steps; the hiring manager owns role clarity and integration; IT supports equipment/access; the new hire participates and raises questions.
Suggested measures | Day-one access readiness; task completion by target date; mandatory orientation completion; unresolved blockers by age; feedback at day 7/15/30.
Data protection | Do not enter identity numbers, bank account details, health information or copies of personal documents in this tracker. Use approved secure systems and follow retention/access policies.
Localisation | Document requirements, right-to-work checks, payroll setup, safety training and policy acknowledgements vary by location and employer. Confirm local law and internal policy before use.
Limitations | This is a generic portfolio template, not legal advice or a claim of an implemented company process.
Pilot approach | Ask HR, a manager and a new hire to review the template; remove irrelevant tasks, assign owners and trial the process before standardising it.